## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | 풍수지리
PROJECT MANAGER | 이석호, 최은지
COMPANY NAME | BOOT4Python
DATE | 2019.01.18 ~ 2019.04.30 | [10 empty] | 제작 준비 | [10 empty] | 프로젝트 계획 및 프로토타입 개발 | [16 empty] | 프로젝트 개발 및 업데이트 | [13 empty] | 프로젝트 최종 실행 및 평가
WBS NUMBER | TASK TITLE | 담당자 | 시작일 | 마감일 | 기간 | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | 프로젝트 역할 분담 | 이준형 | 2019-01-18 | 2019-01-22 | 4 | bar: WEEK 1 F to WEEK 2 F
1.1.1 | 프로젝트 역할 분담_수정 | 이준형 | 2019-01-23 | 2019-01-23 | 1
1.2 | 자료조사: SW | 최은지 | 2019-01-21 | 2019-01-25 | 4
1.3 | 자료조사: HW | 최하림 | 2019-01-21 | 2019-01-25 | 4
1.4 | 수익 분배 | 이준형 | 2019-01-18 | 2019-01-25 | 7 | bar: WEEK 1 F to WEEK 2 F
1.5 | 가이드 라인 | 백이주 | 2019-01-23 | 2019-01-28 | 5 | bar: WEEK 1 W to WEEK 2 F
2 | Project Definition & Planning
2.1 | 프로젝트 범위 및 목표 설정 | 백이주 | 2019-01-23 | 2019-01-25 | 2
2.2 | 예산 계획 | 이준형 | 2019-01-23 | 2019-01-30 | 7 | bar: WEEK 2 M to WEEK 3 W
2.3 | 미팅 장소, 시간 조정 | 이석호 | 2019-01-18 | 2019-01-18 | 0 | bar: WEEK 1 F to WEEK 2 F
2.4 | 한계점 대처 | 최하림 | 2019-01-25 | 2019-01-30 | 5 | bar: WEEK 2 M to WEEK 3 W
2.5 | 프로토타입 개발 | 최은지 | 2019-01-23 | 2019-02-05 | 13 | bar: WEEK 2 M to WEEK 4 T
2.6 | 프로토타입 평가 | 이석호 | 2019-02-05 | 2019-02-15 | 10 | bar: WEEK 4 T to WEEK 5 F
3 | Project Launch & Execution
3.1 | 프로젝트 실행 | 이준형 | 2019-02-18 | 2019-02-25 | 7 | bar: WEEK 6 M to WEEK 7 M
3.1.1 | 결과 예상 | 최하림 | 2019-02-22 | 2019-02-28 | 6 | bar: WEEK 6 F to WEEK 7 R
3.1.2 | 모니터링 | 최은지 | 2019-02-28 | 2019-03-05 | 5 | bar: WEEK 7 R to WEEK 8 T
3.1.3 | 핵심 성과 지표 | 이석호 | 2019-03-04 | 2019-03-11 | 7 | bar: WEEK 8 M to WEEK 9 M
3.2 | 프로젝트 업데이트 | 최은지 | 2019-03-08 | 2019-03-15 | 7 | bar: WEEK 7 T; WEEK 8 F to WEEK 9 F
4 | Project Performance / Monitoring
4.1 | QA(품질보증) | 백이주 | 2019-03-15 | 2019-03-21 | 6 | bar: WEEK 9 F to WEEK 10 R
4.2 | 전체 진행 상황 및 예산 점검 | 이준형 | 2019-03-21 | 2019-03-28 | 7 | bar: WEEK 10 R to WEEK 11 R
4.3 | 프로젝트 최종 실행 | 최은지 | 2019-03-28 | 2019-04-04 | 7 | bar: WEEK 11 R to WEEK 12 F
Formulas:
기간 = DAYS([마감일],[시작일])

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.